## Super Manager
Navigations | Modules | Sub Modules | Status (30-08-2023) | Comments
Side menu | Profile |  | Partially Working | while updating profile in the Mobile number field 0 is already exist and the field name shows Mobile instead of Mobile Number.
OUR SCHOOL | Dashbaord |  | Working
| School Directory | Learner Search | Working
|  | Add Learner | Working | While adding learner, in the Email field emoji's is also getting added. And, while updating the email with the emoji it is not getting updated.
|  | Update Learner | Not Working | While updating learner info after clicking on the update button pop up shows Processing.. please wait but the learner is not getting updated.
|  | Delete Learner | Not Working | After clicking on the Delete icon pop shows Processing please wait but the learner is not getting Deleted. Also, pop up message is coming something went wrong.
|  | Export PDF | Working
| School Attendance | Take Attendance | Partially Working | After marking 2 learners as a Absent and 1 Learner as a Late in the Daily Attendance Report Total number of student shows 40 and Total Present shows 37. Late mark is getting converted into Absent mark value the Total Present learners must be 38.
|  | View Attendance | Partially Working | In view attendance calendar is scrollable for month, does not shows date till 31.
|  | Export Attendance | Working
| School Notice | Add Notice | Not Working | While adding notice after clicking on the Add Notice shows constant Loading animation on the button, notice is not getting added.
|  | Update Notice | Working
|  | Delete Notice | Working
| Our Staff | Add staff | Partially Working | (1). While adding new staff, after adding emoji the Email field it is expecting and Staff gets added successfully. And, in the Name field numberic values also getting updated. (2). While assigning the class to staff and while selecting the class which already assigned to the another staff it shows bottom of update class field this class already asssigned to the xyz user still pop up shows Staff class has been updated successfully.
|  | Update Staff | Partially Working | While updating the Name field it is expecting Numberic value and getting updated successfully.
|  | Delete Staff | Working
|  | Export in pdf | Working
|  | Export in Excel | Working
| School Content | Add Content | Working
|  | Update Content | Not Working | Option not available to update the School Content.
|  | Delete Content | Working
|  | Learner Content | Working
|  | Staff Content | Working | In the content details Shows All Student instead of the All Learners
| Digital Library |  | Working
| Timetable | Create Timetable | Working
|  | Edit Timetable | Working
|  | Delete Timetable | Not Working | In the Timetable list while deleting a particullar Timetable pop shows Timetable deleted successfully but in the Timetable list deleted Timetable is still getting visible.
|  | Class Timetable | Working
|  | Educator Timetable | Working
| Homework | Add Homework | Working
|  | Edit Homework | Working
|  | Delete Homework | Working
|  | View and Download Homework | Working
| School Merit Leaderboard | Add Remarks | Not Working | While Adding remark for the learners after clicking on the Select Category field dropdown is not working.
|  | View Remarks | Not Working | User cannot see the remark before adding.
| School Gen. Info. |  | Partially Working | (1).In the phone number field number was already exist with the 9 and after editing another fields without editing phone number and after clicking in the continue error handling shows in the phone number field that Phone number must start with the 0. (2). In the Facebook link & Instagram link field. Fields are getting updated without url just with the
| School Background Info. |  | Working
| School Management |  | Not Working | After Clicking on the Edit button take to the grey screen and message shows Something went wrong.
| SGB |  | Partially Working | After adding SGB successfully and clicking on the added profile it takes to update the profile but while updating does not shows the added profile picture shows empty in the profile picture field.
| School wall of fame |  | Not Working | After adding profile for the Wall of Fame successfully but added profile is not visible in the School Wall of Fame list.
| Staff Accolades |  | Partially Working | While updating the Staff of the month pop up shows Updated succesfully but not shows successful card and after updating it stays on the page.
| Staff Credentials |  | Working
| Staff Login |  | Working
| Website Messages |  | Working
| Staff Logins |  | Working
| Parent Logins |  | Working
| Result | View Results | Working
|  | Create Test | Working
|  | Edit Marks | Not Working | While editing the marks after clicking on the save changes button shows constant loading animation on the button.
| School Logins |  | Working
| Message Parent |  | Partially Working | After sending the message successfully the sent message is not fetching instantly. After going out and coming back to the module then only sent message is getting visible in the list.
| School Photos and videos |  | Partially Working | Not showing previous added feed images but shows for the newly added feeds for Photos and Videos.
MY CLASS | My Learners | Learner Search
Working
|  | Add Learner | Working | While adding learner, in the Email field emoji's is also getting added. And, while updating the email with the emoji it is not getting updated.
|  | Update Learner | Partially Working | (1). While updating the Name field it is expecting Numberic value and getting updated successfully. (2). After filling the Account Reference Number field and after getting updating successfully but not shows in the Learner persornal info fields shows empty.
|  | Delete Learner | Working
| Class Attendance | Take Attendance | Working
|  | View Attendance | Partially Working | After searching learner by particular name shows mutliple classes for that particular learner of the same name, should shows that learner name which is one in the particular class.
|  | Export Attendance | Working
| My Timetable |  | Working
| Class Notice | Add Notice | Working
|  | Edit Notice | Working
|  | Delete Notice | Working
|  | View and Download Notice | Working
| Class Timetable |  | Working
| Homework | Add Homework | Working
|  | Edit Homework | Working
|  | Delete Homework | Working
|  | View and Download Homework | Working
| School Merit Leaderboard | Add Remarks | Not Working | While Adding remark for the learners after clicking on the Select Category field dropdown is not working.
|  | View Remarks | Not Working | User cannot see the remark before adding.
| Class Message |  | Working
| Class Content | Add Content | Working
|  | Update Content | Working
|  | Delete Content | Working
|  | Learner Content | Working
| Academic Calendar |  | Working
| Parent Logins |  | Working
Events |  |  | Working
Community | Dictionary |  | Not Working | Cannot find out difficult words and need much validation for this module.
| Scientific Calculator |  | Partially Working
| Circuit and District News |  | Not Working | News is getting added successfully from the vhembewest backend but not visible in the Circuit and District news module.
| District Events |  | Not Working | District event is getting added successfully from the vhembewest backend but not visible in the District event module.
| University Brochure |  | Working
Resources | Teacher's Resources | Annual Teaching Plan | Working
|  | Staff Contents | Partially Working | While adding content for the staff also shows the option to add content learners. School Content UI is getting visible in the Staff content module.
| Learner's Resources | NSC Exam Past Papers | Working
|  | Exam Guide | Working
|  | HMC Papers | Working
|  | Mind The Gap | Working

## Parent
Navigations | Modules | Sub Modules | Status (30-08-2023 | Comments
Side menu | Profile | View and edit Information
Working
OUR SCHOOL | Dashbaord | View and edit Information | Working
| School Notice | View Notice
Working
|  | Notice List | Working
|  | Notice details | Working
| Our Staff | View Staff | Working
|  | Staff List | Working
| Digital Library | Ebooks | Working
|  | Spelling Bee | Working
|  | 4 to 7 papers | Working
|  | View and download | Working
| School Gen. Info. | View Information and email other links | Working
| School Background Info. | View Information | Working
| School Management | View Information | Working
| SGB | View Information | Working
| School wall of fame | View sort and apply filter | Working
| School Photos and videos | View, Play, like and dislike photos and videos | Working
| Message Parent | view message | Not working | message sent but not recieved at parent side
Sibling page | Sibling list | View Profile | Partially Working | profile image is taking time to load
| Profile | View Profile | Partially Working | taking time lot of load
| Class Timetable | View Weekly Timetable | Working | taking time lot of load
| Homework | View list | Working | taking time lot of load
|  | View Description | Working
| Digital Library | View and download | Working
| Message Teacher | teacher recieving message | Working | taking time lot of load
|  | Send Message | Working | taking time lot of load
| Class Notice | View notice list and description | Partially Working | taking time lot of load
| Academic Calendar | view Timetable | Working
| Digital Content | View Modules | Working | taking time lot of load
|  | Assignment View download | Working
|  | Curriculum | Working
|  | Other Download | Working
|  | Study Material | Working
| Quiz | Not yet developed
| Scientific Calculator | Calculations | Working
| Dictionary | view and search | Working
| Report | Not yet developed
Events |  | View and download | Working
Community | Dictionary | view and search | Working
| Scientific Calculator | Calculations | Working
| Circuit and District News | something went wrong | Not working
| District Events | View Description | Working
| University Brochure | View and download | Working

## Educator
Navigations | Modules | Sub Modules | Status | Comments
Side Menu |  |  | Partially Working | Designation shows "Educators" instead of "Educator"
OUR SCHOOL | School Directory | Search by Class | Working | Attachment is not downloading
|  | Search by Name | Partially Working | Cannot able to search by full name
|  | Learenr Add | Feature not available
|  | Learner Update | Working
|  | Learner Delete | Working
|  | Export in PDF | Not Working
| Attendance | Take Attendance | Working
|  | View Attendance | Working
|  | Export Attendance | Not Working
| School Notice |  | Working
| Our Staff |  | Partially Working | Designation shows "Educators" instead of "Educator"
| Digital Content | Learner Content | Working | Content detail page: Change Students to Learners
Staff Content
| Homework | Homework List | Working
|  | Homework Details | Working
|  | Add Homework | Working
| Digital Library | E-books | Working
|  | Spelling Bee | Working
|  | 4 to 7 Papers | Working
| Timetable | Timetable Setup | Working
|  | Classes Timetable | Working
|  | Educator Timetable | Working
| School General Info |  | Working
| School Background Information |  | Working
| School Management |  | Working
| SGB |  | Working
| School Wall of Fame |  | Working
| School Photos and Videos |  | Partially Working | Images/videos is not showing
Message Parent
My Class | My Learners | Add Learner | Working
|  | Update Learner | Working
|  | Delete Learner | Working
|  | Export in PDF | Not Working
| Class Attendance | Take Attendance | Working
|  | View Attendance | Working
|  | Export Attendance | Not Working
| My Timetable |  | Working
| Class Notice | Add Notice | Working
|  | Update Notice | Working
|  | Delete Notice | Working
| Class Timetable |  | Working
| Homework | Add Homework | Working
|  | Update Homework | Working
|  | Delete Homework | Working
| Class Merit Leaderboard | Add Remarks | Not Working | Category drop down shows nothing and it is mandatory
|  | View Remarks | Not Working | Server Error
| Class Message |  | Working
| Class Content | Add Content | Working
|  | Update Content | Feature not available
|  | Delete Content | Feature not available
| Academic Calendar |  | Working
| Parent Login |  | Working
Events |  |  | Working
Community | Dictionary |  | Working
| Scientific Calculator |  | Not Working | 1. If calculation is long it shows. 2. If we add/subtract/divide/multiply 2 numbers, then we cannot able to modify the 1st number we have added
| Circuit and District News |  | Working
| District Events |  | Working
| University Brochure |  | Working
Resources | Teacher's Resources | Annual Teaching Plan | Working
|  | Staff Contents | Working
| Learner's Resources | NSC Exam Past Papers | Working
|  | Exam Guide | Working
|  | HMC Papers | Working
|  | Mind The Gap | Working

## Management
Navigations | Modules | Sub Modules | Status (30-08-2023) | Comments
Side Menu | Profile | View Profile | Working
|  | Update Profile | Working
|  | Update Class | Working
|  | Update Subject | Working
| Visit School Website |  | Working
| Settings | Data & Privacy | Working
OUR SCHOOL | Dashbaord
| School Directory | Learner Search by Class | Working
|  | Learner Search by Name | Partially Working | Cannot able to search by full name
| School Attendance | Take Attendance | Partially Working | The late mark in the daily attendance report after marking attendance they are also counted as absent.
|  | View Attendance | Working
|  | Export Attendance | Working
| School Notice | View Notice | Working
| Our Staff | Staff List | Working
|  | Learner Content | Working | Content detail page: Change Students to Learners
|  | Staff Content | Working
| Digital Library |  | Working
| Timetable | Create Timetable | Working
|  | Edit Timetable | working
|  | Delete Timetable | working
|  | Timetable List | Working
|  | Class Timetable | working
|  | Educator Timetable | working
| Homework | Add Homework | working
|  | Edit Homework | working
|  | Delete Homework | working
|  | View and Download Homework | working
| School Merit Leaderboard | Add Remarks | Not Working | In Add Merit/Demerit Section While Adding Merit/Demerit Select Category Section is not working because of that we are not able to add merit/Demerit.
|  | View Remarks | Not Working | User cannot see the remark before adding.
| School Gen. Info. |  | working
| School Background Info. |  | working
| School Management |  | working
| SGB |  | working
| School wall of fame |  | working
| My Learners | Learner Search by Name | Working
|  | Add Learner | Partially Working | While Adding the learner it also accept emojis and special Characters in all field
|  | Update Learner | Partially Working | While Updating the learner it also accept emojis and special Characters in all field
|  | Delete Learner | Working
| Class Attendance | Take Attendance | Partially Working | The late mark in the daily attendance report after marking attendance they are also counted as absent.
|  | View Attendance | Working
|  | Export Attendance | Working
| My Timetable |  | Working
| Class Notice | Add Notice | Working
|  | Edit Notice | Working
|  | Delete Notice | Working
|  | View and Download Notice | Working
| Class Timetable |  | Working
| Homework | Add Homework | Working
|  | Edit Homework | Working
|  | Delete Homework | Working
|  | View and Download Homework | Working
| School Merit Leaderboard | Add Remarks | Not Working | In Add Merit/Demerit Section While Adding Merit/Demerit Select Category Section is not working because of that we are not able to add merit/Demerit.
|  | View Remarks | Not Working
Class Message
| Class Content | Add Content | Working
|  | Update Content | Option not available
|  | Delete Content | Option not available
| Academic Calendar |  | Working
| Parent Logins |  | Working
Events |  |  | Working
Community | Dictionary |  | Working
| Scientific Calculator |  | Not Working | 1. If calculation is long it shows. 2. If we add/subtract/divide/multiply 2 numbers, then we cannot able to modify the 1st number we have added
| Circuit and District News |  | Working
| District Events |  | Working
| University Brochure |  | Working
Resources | Teacher's Resources | Annual Teaching Plan | Working
|  | Staff Contents | Working
| Learner's Resources | NSC Exam Past Papers | Working
|  | Exam Guide | Working
|  | HMC Papers | Working
|  | Mind The Gap | Working

## UAT Major bugs
Super Manager | Modules | Sub Modules | Status (30-08-2023) | Comments
| School Directory | Add Learner | Working | While adding learner, in the Email field emoji's is also getting added. And, while updating the email with the emoji it is not getting updated.
|  | Update Learner | Not Working | While updating learner info after clicking on the update button pop up shows Processing.. please wait but the learner is not getting updated.
|  | Delete Learner | Not Working | After clicking on the Delete icon pop shows Processing please wait but the learner is not getting Deleted. Also, pop up message is coming something went wrong.
| School Notice | Add Notice | Not Working | While adding notice after clicking on the Add Notice shows constant Loading animation on the button, notice is not getting added.
Timetable
|  | Delete Timetable | Not Working | In the Timetable list while deleting a particullar Timetable pop shows Timetable deleted successfully but in the Timetable list deleted Timetable is still getting visible.
| School Management |  | Not Working | After Cliciking on the Edit button take to the grey screen and message shows Something went wrong.
| School Photos and videos |  | Partially Working | Not showing previous added feed images but shows for the newly added feeds for Photos and Videos.
| Teacher's Resources | Staff Contents | Partially Working | While adding content for the staff also shows the option to add content learners. School Content UI is getting visible in the Staff content module.
Educator | Modules | Sub Modules | Status (30-08-2023) | Comments
Our School | School Photos and Videos |  | Not Working | Images/videos is not showing
| School Directory | Export in PDF | Not Working | Attachment not downloading
| School Attendance | Export Attendance | Not Working | Attachment is not downloading
My Class | My Learners | Export in PDF | Not Working | Attachment is not downloading for PDF
| Class Attendance | Export Attendance | Not Working | Attachment is not downloading for PDF as well as Excel
| Class Merit Leaderboard | Add Remarks | Not Working | Category drop down shows nothing and it is mandatory
Management | Modules | Sub Modules | Status (30-08-2023) | Comments
| School Attendance | Take Attendance | Partially Working | The late mark in the daily attendance report after marking attendance they are also counted as absent.
| School Merit Leaderboard(Our School) | Add Remarks | Not Working | In Add Merit/Demerit Section While Adding Merit/Demerit Select Category Section is not working because of that we are not able to add merit/Demerit.
|  | View Remarks | Not Working | User cannot see the remark before adding.
| School Directory | Learner Search by Name | Partially Working | Cannot able to search by full name
| My Learners | Add Learner | Partially Working | While Adding the learner it also accept emojis and special Characters in all field
|  | Update Learner | Partially Working | While Updating the learner it also accept emojis and special Characters in all field
| Class Attendance | Take Attendance | Partially Working | The late mark in the daily attendance report after marking attendance they are also counted as absent.
| School Merit Leaderboard(My Class) | Add Remarks | Not Working | In Add Merit/Demerit Section While Adding Merit/Demerit Select Category Section is not working because of that we are not able to add merit/Demerit.
|  | View Remarks | Not Working | User cannot see the remark before adding.
| Scientific Calculator |  | Not Working | 1. If calculation is long it shows. 2. If we add/subtract/divide/multiply 2 numbers, then we cannot able to modify the 1st number we have added
Parent | Modules | Sub Modules | Status (30-08-2023) | Comments
our school | Message Parent | view message | Not working | message sent but not recieved at parent side
sibling page | Sibling list | View Profile | Partially Working | profile image is taking time to load
community | Circuit and District News |  | Not working | something went wrong